## Tasks
ID | Task | Phase | Track | Owner | Start | Due | Est (days) | Depends on | Status | % complete | Actual days | Notes
D0.1 | Confirm Postgres tier and region (B1ms, West US 3); raise the request | 0 - Decisions | Platform | Dev A | 2026-10-12 | 2026-10-12 | 0.25 |  | Not started | 0%
D0.2 | Decide SWA linked-backend vs explicit CORS - spike both, pick one | 0 - Decisions | Application | Dev B | 2026-10-12 | 2026-10-13 | 0.5 |  | Not started | 0%
D0.3 | Start the Azure OpenAI / BAA conversation with legal - long lead | 0 - Decisions | Platform | Dev A | 2026-10-12 | 2026-10-12 | 0.25 |  | Not started | 0%
D0.4 | Agree environment names and the staging story (slot vs second RG) | 0 - Decisions | Both | Dev A + B | 2026-10-13 | 2026-10-13 | 0.25 |  | Not started | 0%
D0.5 | Confirm the pilot runs on the fictional corpus - write the gate down | 0 - Decisions | Both | Dev A + B | 2026-10-13 | 2026-10-13 | 0.25 |  | Not started | 0%
D0.7 | ASK THE CLIENT: data volume, source system, export format, a sample | 0 - Decisions | Both | Dev A + B | 2026-10-12 | 2026-10-13 | 0 |  | Not started | 0% |  | COSTS NOTHING, WORTH THE MOST - the answer sizes all of Phase 6
A1.1 | Provision Postgres Flexible Server B1ms, private endpoint, firewall | 1 - Postgres | Platform | Dev A | 2026-10-14 | 2026-10-14 | 0.5 | D0.1 | Not started | 0%
A1.2 | Enable PITR (7 day); confirm automated backup schedule | 1 - Postgres | Platform | Dev A | 2026-10-14 | 2026-10-14 | 0.25 | A1.1 | Not started | 0%
A1.3 | Create DB, role, least-privilege grants - app user is not owner | 1 - Postgres | Platform | Dev A | 2026-10-15 | 2026-10-15 | 0.5 | A1.1 | Not started | 0%
B1.1 | Run all 15 migrations against Postgres; fix dialect assumptions | 1 - Postgres | Application | Dev B | 2026-10-14 | 2026-10-15 | 1 | A1.1 | Not started | 0%
B1.2 | Run the full backend suite against Postgres, not SQLite | 1 - Postgres | Application | Dev B | 2026-10-15 | 2026-10-15 | 0.5 | B1.1 | Not started | 0%
B1.3 | Corpus loader: ingest into Postgres, repeatable and idempotent | 1 - Postgres | Application | Dev B | 2026-10-15 | 2026-10-16 | 1 | B1.1 | Not started | 0%
B1.4 | Decide backup.py's fate - SQLite-only, already no-ops elsewhere | 1 - Postgres | Application | Dev B | 2026-10-16 | 2026-10-16 | 0.25 | B1.1 | Not started | 0%
A1.4 | Size the asyncpg pool against the B1ms connection limit | 1 - Postgres | Platform | Dev A | 2026-10-16 | 2026-10-16 | 0.5 | B1.1 | Not started | 0%
A1.5 | CI runs the suite against Postgres, not SQLite - service container | 1 - Postgres | Platform | Dev A | 2026-10-16 | 2026-10-16 | 0.5 | B1.2 | Not started | 0% |  | DO NOT CUT - without it CI tests a database you no longer use
B1.5 | Documented rollback to SQLite if Postgres fails mid-pilot | 1 - Postgres | Application | Dev B | 2026-10-16 | 2026-10-16 | 0.5 | B1.1 | Not started | 0%
M1 | MILESTONE: app runs on Postgres, suite green | 1 - Postgres | Both | Dev A + B | 2026-10-16 | 2026-10-16 | 0 | A1.4,B1.3 | Not started | 0%
A2.1 | Provision Static Web App (Standard) - nanovox-web | 2 - Split | Platform | Dev A | 2026-10-19 | 2026-10-19 | 0.5 | D0.2 | Not started | 0%
A2.2 | Rename/retarget App Service as API-only - nanovox-api | 2 - Split | Platform | Dev A | 2026-10-19 | 2026-10-19 | 0.5 |  | Not started | 0%
A2.3 | Wire SWA linked backend; confirm /api/* proxies same-origin | 2 - Split | Platform | Dev A | 2026-10-20 | 2026-10-20 | 0.5 | A2.1,A2.2 | Not started | 0%
B2.1 | Frontend build artefact independent of the backend package | 2 - Split | Application | Dev B | 2026-10-19 | 2026-10-20 | 1 | D0.2 | Not started | 0%
B2.2 | CORS middleware + CORS_ORIGINS - fallback if A2.3 fails | 2 - Split | Application | Dev B | 2026-10-20 | 2026-10-21 | 0.75 | A2.3 | Not started | 0% |  | FALLBACK CUT 3 - disappears on its own if the linked backend works
B2.3 | Keep spa.py working for local/container; test it still serves | 2 - Split | Application | Dev B | 2026-10-21 | 2026-10-21 | 0.5 |  | Not started | 0%
A2.4 | One pipeline, two deploy stages: build both, deploy API then web | 2 - Split | Platform | Dev A | 2026-10-21 | 2026-10-23 | 1.5 | A2.3,B2.1 | Not started | 0%
A2.5 | Deploy ordering + rollback: API first, web second, both revertible | 2 - Split | Platform | Dev A | 2026-10-23 | 2026-10-23 | 0.5 | A2.4 | Not started | 0%
A2.6 | Authentication after the split - where sign-in lives, SWA vs API | 2 - Split | Platform | Dev A | 2026-10-26 | 2026-10-27 | 1.5 | A2.3 | Not started | 0% |  | The plan previously never mentioned authentication at all
M2 | MILESTONE: both resources deploy from one pipeline run, signed in | 2 - Split | Both | Dev A + B | 2026-10-27 | 2026-10-27 | 0 | A2.5,B2.2,A2.6 | Not started | 0%
A3.1 | Key Vault + system-assigned managed identity on the API | 3 - Hardening | Platform | Dev A | 2026-10-28 | 2026-10-28 | 0.5 |  | Not started | 0%
A3.2 | Move OPENAI_API_KEY and DATABASE_URL to Key Vault references | 3 - Hardening | Platform | Dev A | 2026-10-29 | 2026-10-29 | 0.5 | A3.1 | Not started | 0%
A3.3 | Application Insights on the API; connection string via Key Vault | 3 - Hardening | Platform | Dev A | 2026-10-30 | 2026-10-30 | 0.5 | A3.1 | Not started | 0%
A3.4 | Staging slot on the API; pipeline deploys to staging then swaps | 3 - Hardening | Platform | Dev A | 2026-11-02 | 2026-11-03 | 1 | A2.4 | Not started | 0% |  | DO NOT CUT - staging slot is the rollback path
A3.5 | Alerts: availability, 5xx rate, p95 latency, DB connection failures | 3 - Hardening | Platform | Dev A | 2026-11-04 | 2026-11-05 | 0.75 | A3.3 | Not started | 0%
B3.1 | Structured request logging with correlation id into App Insights | 3 - Hardening | Application | Dev B | 2026-10-28 | 2026-10-29 | 0.75 | A3.3 | Not started | 0%
B3.2 | Health endpoint reports DB and provider reachability for probes | 3 - Hardening | Application | Dev B | 2026-10-29 | 2026-10-30 | 0.5 |  | Not started | 0%
B3.3 | /risk payload 204 KB - split or trim before real volume | 3 - Hardening | Application | Dev B | 2026-11-02 | 2026-11-03 | 1.5 |  | Not started | 0% |  | FALLBACK CUT 1 - only if the week-3 check-in is behind. 204 KB works today.
B3.4 | Rate limiting on /insights/generated - it costs money per call | 3 - Hardening | Application | Dev B | 2026-11-06 | 2026-11-06 | 0.5 |  | Not started | 0%
A3.6 | Azure budget alert on the subscription, and on OpenAI spend | 3 - Hardening | Platform | Dev A | 2026-11-09 | 2026-11-09 | 0.25 |  | Not started | 0%
M3 | MILESTONE: staging swap works, telemetry flowing, alerts fire | 3 - Hardening | Both | Dev A + B | 2026-11-06 | 2026-11-06 | 0 | A3.5,B3.4 | Not started | 0%
A4.1 | Restore drill: restore Postgres from PITR into a scratch server | 4 - Cutover | Platform | Dev A | 2026-11-09 | 2026-11-09 | 0.75 | A1.2 | Not started | 0% |  | DO NOT CUT - a pilot without a tested restore is an outage with an audience
A4.2 | Runbook: deploy, roll back, restore, rotate a secret, read an alert | 4 - Cutover | Platform | Dev A | 2026-11-10 | 2026-11-11 | 1 | A3.5 | Not started | 0% |  | DO NOT CUT - the runbook is what makes the rota possible
A4.3 | Entra sign-in re-enabled and tested for the pilot audience | 4 - Cutover | Platform | Dev A | 2026-11-12 | 2026-11-12 | 0.5 |  | Not started | 0%
B4.1 | Load test: 20 concurrent readers against /exec and /risk | 4 - Cutover | Application | Dev B | 2026-11-09 | 2026-11-10 | 1 | B3.3 | Not started | 0% |  | FALLBACK CUT 2 - replace with a 30-min smoke under concurrency
B4.2 | Full acceptance pass - nine screens, write path, CSV export | 4 - Cutover | Application | Dev B | 2026-11-11 | 2026-11-12 | 0.75 |  | Not started | 0%
B4.3 | Error budget check: no unhandled 5xx in 48 h of staging | 4 - Cutover | Application | Dev B | 2026-11-12 | 2026-11-13 | 0.5 | A3.4 | Not started | 0%
M4 | MILESTONE: dress rehearsal - deploy, swap, verify, roll back | 4 - Cutover | Both | Dev A + B | 2026-11-13 | 2026-11-13 | 0.5 |  | Not started | 0%
A4.4 | Production cutover | 4 - Cutover | Both | Dev A + B | 2026-11-19 | 2026-11-19 | 0.5 | M4,B4.4 | Not started | 0%
A4.6 | Decide RG-NanoVox-POC's fate - torn down, or kept as staging | 4 - Cutover | Platform | Dev A | 2026-11-17 | 2026-11-17 | 0.25 |  | Not started | 0%
B4.4 | CLIENT ACCEPTANCE: the client signs off, not a developer | 4 - Cutover | Both | Dev A + B | 2026-11-16 | 2026-11-17 | 0.5 | M4 | Not started | 0% |  | DO NOT CUT - a developer's acceptance is not the client's
A4.5 | Buffer / contingency | 4 - Cutover | Both | Dev A + B | 2026-11-20 | 2026-11-20 | 1 |  | Not started | 0%
P1 | Move from OpenAI to Azure OpenAI under a signed BAA | 5 - PHI (outside window) | Platform | TBD |  |  | 6.5 | D0.3 | Not started | 0%
P2 | De-identification before any model call | 5 - PHI (outside window) | Application | TBD |  |  | 6.5 |  | Not started | 0%
P3 | Encryption and key management review | 5 - PHI (outside window) | Platform | TBD |  |  | 2.5 |  | Not started | 0%
P4 | Access control and audit logging | 5 - PHI (outside window) | Application | TBD |  |  | 5 |  | Not started | 0%
P5 | Retention and deletion, including backups and the stage cache | 5 - PHI (outside window) | Application | TBD |  |  | 4 |  | Not started | 0%
P6 | Private networking - VNet, private endpoints (design with P1) | 5 - PHI (outside window) | Platform | TBD |  |  | 3.5 | P1 | Not started | 0%
P7 | SOC 2 readiness assessment (not development) | 5 - PHI (outside window) | Compliance | TBD |  |  | 0 |  | Not started | 0%
P8 | Change management evidence | 5 - PHI (outside window) | Platform | TBD |  |  | 2 |  | Not started | 0%
P9 | Incident response plan and on-call | 5 - PHI (outside window) | Platform | TBD |  |  | 2 |  | Not started | 0%
P10 | Vendor management register | 5 - PHI (outside window) | Compliance | TBD |  |  | 1 |  | Not started | 0%
P11 | Penetration test (external, 2-4 weeks lead) | 5 - PHI (outside window) | Compliance | TBD |  |  | 0 |  | Not started | 0%
R1 | Obtain a real data sample and its format from the client | 6 - Real data (outside window) | Both | TBD |  |  | 0 | D0.7 | Not started | 0%
R2 | TranscriptSource adapter for the client's real format | 6 - Real data (outside window) | Application | TBD |  |  | 7.5 | R1 | Not started | 0% |  | Cannot be estimated properly until R1 lands a sample. 7.5 d is a placeholder.
R3 | Re-size Postgres, App Service and /risk against real volume | 6 - Real data (outside window) | Platform | TBD |  |  | 2 | R1 | Not started | 0%
R4 | Model the extraction cost at real volume before running it | 6 - Real data (outside window) | Both | TBD |  |  | 1 | R1 | Not started | 0%
R5 | Data onboarding runbook and a repeatable re-ingest path | 6 - Real data (outside window) | Application | TBD |  |  | 2 | R2 | Not started | 0%
R6 | UAT with the client on real data | 6 - Real data (outside window) | Both | TBD |  |  | 2 | R2,R5 | Not started | 0%
R7 | Define and agree an uptime target, and measure against it | 6 - Real data (outside window) | Platform | TBD |  |  | 1 |  | Not started | 0%

## Summary
NanoVox Insights - production readiness
12 Oct - 20 Nov 2026 ¦ 6 weeks ¦ 2 developers, part time ¦ 30 person-days
By phase
Phase | Tasks | Est (days) | Done | In progress | Blocked | % complete
0 - Decisions | 6 | 1.5 | 0 | 0 | 0 | 0%
1 - Postgres | 11 | 5.5 | 0 | 0 | 0 | 0%
2 - Split | 10 | 7.25 | 0 | 0 | 0 | 0%
3 - Hardening | 11 | 6.75 | 0 | 0 | 0 | 0%
4 - Cutover | 11 | 7.25 | 0 | 0 | 0 | 0%
5 - PHI (outside window) | 11 | 33 | 0 | 0 | 0 | 0%
6 - Real data (outside window) | 7 | 15.5 | 0 | 0 | 0 | 0%
Total | 67 | 76.75 | 0 | 0 | 0 | 0%
Capacity check
In-window estimate (Phases 0-4) | 28.25
Capacity: 30 working days x 2 devs x 50% | 30
Headroom (days) | 1.75
Phase 5 - PHI, not in this window | 33
Phase 6 - real data, not in this window | 15.5
By track
Track | Tasks | Est (days) | Done | % complete
Platform | 30 | 33.25 | 0 | 0%
Application | 21 | 36.5 | 0 | 0%
Both | 13 | 6 | 0 | 0%
Compliance | 3 | 1 | 0 | 0%
Effort
Estimated (all phases) | 76.75
Actual logged | 0
Variance (actual - estimate) | -76.75
How to use this
Edit only the yellow cells: Status, % complete, Actual days, Notes.
Everything on this sheet is a formula and follows automatically.
Green rows are milestones. Amber rows are gates - a gate not met blocks what follows.
Phase 5 carries no dates: it is outside this window and starts with a contract, not code.
The hard rule: no production PHI until P1-P6 are Done.